## Summary
IT Team Task List
S.No. | Task Name | Phase | Remarks | Discussion Date | Start Date | Due Date | Completion Date | Status
1 | LEAD MANAGEMENT | Survey Cal + Lead DB | Linking & Table View | 2018-11-21 | 2018-12-01 | 2018-12-06 |  | In Progress
|  | Lead DB Edit | Dynamic with Survey Cal | 2018-11-21 | 2018-12-07 | 2018-12-11 |  | Not Started
|  | Direct Lead Additions | Dynamic with Survey Cal + Email Notifications | 2018-11-21 | 2018-12-12 | 2018-12-18 |  | Not Started
|  | Reminders | FUPs & Surveys via Email & System Pop-Ups | 2018-11-21 | 2018-12-19 | 2018-12-21 |  | Not Started
|  | Reminders 2 | All reminders via SMS / WhatsApp | 2018-11-21 | 2018-12-22 | 2018-12-24 |  | Not Started
2 | WEBSITE CHANGES & ADDITIONS | Designer Wall Shades | All colors to be shown in both base & top | 2018-11-01 |  |  |  | In Progress
|  | Enamel Paint Addition | To be added in wall finishes @ LS rates | 2018-11-01 |  |  |  | In Progress
|  | Ceiling Color | 2 Colors for Ceiling (Snow & Supeior) & Border (All Non HD) | 2018-11-01 |  |  |  | In Progress
|  | Room Wise Additions | Wall Shades + DWs + HDs | 2018-11-01 |  |  |  | In Progress
|  | Extra Items | Custom Name Fields (Wall + Wood) | 2018-11-01 |  |  |  | In Progress
3 | BACKEND CHANGES & ADDITIONS | Designer Walls shades & consumptions | Consumption matrix to be updated with emails | 2018-11-23 |  |  |  | Not Started
|  | Room Wise Additions | Consumption matrix to be updated with emails | 2018-11-23 |  |  |  | Not Started
|  | Wooden Orders Consumption Matrix | To be updated as advised based upon number / area | 2018-11-23 |  |  |  | Not Started
|  | Localized Putty Consumption | Calculation as per area for all BHKs | 2018-11-23 | 2018-11-28 | 2018-11-30 | 2018-11-30 | Completed
|  | Rounding Off Entries | All values to be rounded off to no decimal place | 2018-11-23 | 2018-11-28 | 2018-11-30 | 2018-11-30 | Completed
4 | MANUAL ORDER CHANGES & ADDITIONS | Designer Wall Shades | Ability to add (Front + Back End Features & Notifications) | 2018-11-23 | 2018-11-28 | 2018-11-30 | 2018-11-30 | Completed
|  | Enamel Paint Addition | Ability to add (Front + Back End Features & Notifications) | 2018-11-23 |  |  |  | Not Started
|  | Ceiling Color | Ability to add (Front + Back End Features & Notifications) | 2018-11-23 |  |  |  | Not Started
|  | Room Wise Additions | Ability to add (Front + Back End Features & Notifications) | 2018-11-23 |  |  |  | Not Started
|  | Extra Items | Ability to add (Front + Back End Features & Notifications) | 2018-11-23 |  |  |  | Not Started
|  | Order Modification (Wall & Wood) | Editing of generated order with notification emails | 2018-11-23 |  |  |  | Not Started
5 | DEALER MODULE | Dealer Addition | By AM & Welcome Mail to Dealer + GM | 2018-11-01 | 2018-11-02 | 2018-11-06 | 2018-11-06 | Completed
|  | Customer Addition | By Dealer | 2018-11-01 | 2018-11-02 | 2018-11-06 | 2018-11-06 | Completed
|  | Notification Emails | Notification Email to AM & GM on Customer Addition | 2018-11-26 | 2018-11-26 | 2018-11-26 | 2018-11-26 | Completed
6 | PAYMENT VERIFICATION | Verification | Dropdown to verify payment received + Notification Emails | 2018-11-01 |  |  |  | Not Started
|  | Notification Emails | Order Value, Amount Received & Pending (Every Entry) | 2018-11-01 |  |  |  | Not Started
|  | Order Creation Email | To be sent once pending payment = 0 | 2018-11-01 |  |  |  | Not Started
Note on F7: user: All reminders via SMS (WhatsApp Later)
Note on C18: user: As discussed, color shades added for front end for all the bhk1 to bhk6. for both Mannual & website Calculator

## Lead Management
Lead Management Phase Overview
S.No. | Phase | Description | Working Days
1 | Survey Cal + Lead DB | Lead comes form survey calander form and displays on the lead table / DB addition | 5
2 | Lead DB Edit | Editing lead in DB should reflect in Survey Cal | 4
3 | Direct Lead Additions | Lead to be added in survey cal by direct form if status = survey requested with email notifications | 6
4 | Reminders (a) | All Follow Ups & Surveys via email | 1
5 | Reminders (b) | All Follow Ups & Surveys via System Popups for CCAs | 2
6 | Reminders 2 | All reminders via SMS (WhatsApp Later) | 2
Total Working Days |  |  | 20